## Sheet1
Styling & HTML | Efforts | Completion Date | Cost 50/hr
Login | 16 | 2019-02-01 | 800
Track Recod 1 | 32 | 2019-06-01 | 1600
Track Record 2 | 24 | 2019-09-01 | 1200
Pre Report Page | 24 | 2019-12-01 | 1200
Report Page | 40 | 17/1/2019 | 2000
Image Upload | 16 | 19/1/2019 | 800
Notification/Messages/Alerts | 16 | 21/1/2019 | 800
|  | Total Cost | 8400
Efforts
Project Development | React | API | Testing | Total Hrs | Completion Date | Cost 80/hr
Project Setup | 8 | 8 | 0 | 16 | 2019-01-01 | 1280
Login | 12 | 12 | 8 | 32 | 2019-06-01 | 2560
Track Recod 1 | 48 | 40 | 16 | 104 | 20/1/2019 | 8320
Track Record 2 | 40 | 32 | 16 | 88 | 2019-01-02 | 7040
Pre Report Page | 24 | 0 | 8 | 32 | 2019-07-02 | 2560
Report Page | 96 | 64 | 24 | 184 | 2019-06-03 | 14720
Image Upload | 48 | 64 | 16 | 128 | 24/3/2019 | 10240
Print | 48 | 24 | 16 | 88 | 2019-01-04 | 7040
[5 empty] | Total Cost | 53760
Admin Panel | Efforts | Testing | Total Hrs | Cost 80/hr
Type of work | 48 | 16 | 64 | 5120
Unit | 24 | 8 | 32 | 2560
Supervisors | 24 | 8 | 32 | 2560
Work | 16 | 8 | 24 | 1920
Workes | 24 | 8 | 32 | 2560
Grade | 16 | 8 | 24 | 1920 | Date Completion
|  |  | Total Cost | 16640 | 2019-10-04
Project Deployment | Efforts | Cost
API Setup & Installation | 24 | 1920
App Setup & Installation | 24 | 1920
| Total Cost | 3840
| Final Live Date | 15/4/2019
Summary | Cost
Styling & Html | 8400
Project Development | 53760
Admin Panel | 16640
Project Deployement | 3840
Total Cost of the Project | 82640

## Sheet2
Screens | Sub Modules | Date | Module Completion Date
Login |  | Done
Work Arrangement | Add/Edit | 2019-04-07
| Preview | 2019-04-09
| Summary | 2019-04-11 | 2019-04-11
Attendance | Add/Edit | 2019-04-15
| Summary | 2019-04-17 | 2019-04-17
Work Request | Add/Edit | 2019-04-21
| Upload Photo | 2019-04-24
| Preview | 2019-04-26
| Summary | 2019-04-27 | 2019-04-27
Daily Work Track | Add/Edit | 2019-05-01
| Summary | 2019-05-03
| Preview | 2019-05-05 | 2019-05-05
Report | Form | 2019-05-08
| Report page for Supervisor | 2019-05-16
| Report page for Site & Supervisor | 2019-05-21 | 2019-05-21
Admin Panel | Type of work | 2019-05-25
| Unit | 2019-05-27
| Supervisors | 2019-05-29
| Work | 2019-06-01
| Workes | 2019-06-03
| Grade | 2019-06-05 | 2019-06-05